## Project Details
Project Name | Project Spacetrek
Project Sponsor
Project Manager
Start Date | 2024-01-17
Expected End Date | 2025-02-17
Estimated Duration (Wk) | 57

## Gantt Chart
[7 empty] | Year | 2024 |  |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  |  | 2024 |  |  |  | 2024 |  |  |  | 2024 |  |  |  |  | 11 |  |  |  | 12
[7 empty] | Month | 2024-01-08 |  |  |  |  | 2024-02-12 |  |  |  | 2024-03-11 |  |  |  | 2024-04-08 |  |  |  |  | 2024-05-13 |  |  |  | 2024-06-10 |  |  |  | 2024-07-08 |  |  |  |  | 2024-08-12 |  |  |  | 2024-09-09 |  |  |  | 2024-09-09 |  |  |  |  | 2024-11-11 |  |  |  | 2024-12-09
[7 empty] | Date | 2024-01-01 | 2024-01-08 | 2024-01-15 | 2024-01-22 | 2024-01-29 | 2024-02-05 | 2024-02-12 | 2024-02-19 | 2024-02-26 | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11 | 2024-11-18 | 2024-11-25 | 2024-12-02 | 2024-12-09 | 2024-12-16 | 2024-12-23
[7 empty] | Week | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
ID | Activity | Assigned To | Duration | Start Date | End Date | Status | %
1 | Activity 01 | Resource Name 01 | 5 | 2024-01-17 | 2024-01-22 | WIP | 10% |  |  |  | C
2 | Activity 02 | Resource Name 02 | 2 | 2024-01-20 | 2024-01-22 | WIP | 40%
3 | Activity 03 | Resource Name 03 | 10 | 2024-02-04 | 2024-02-14 | Pending
4 | Activity 04 | Resource Name 04 | 6 |  |  | On Hold
5 | Activity 05
6 | Activity 06
7 | Activity 07
8 | Activity 08
9 | Activity 09
10 | Activity 10
11 | Activity 11
12 | Activity 12
13 | Activity 13
Formulas:
End Date = [Start Date]+[Duration]

## Sheet7
Task Status List
Pending
WIP
On Hold
Completed
Under Review

## Team
ID | Name | Role | Cost
1 | Resource Name 01 | Engineering Manager | 30
2 | Resource Name 02 | Project Manager | 20
3 | Resource Name 03 | Project Lead | 10
4 | Resource Name 04 | Design Engineer | 5
5 | Resource Name 05 | Design Engineer | 5
6 | Resource Name 06 | Design Engineer | 5
7 | Resource Name 07 | Design Engineer | 5
8 | Resource Name 08 | Sr Design Engineer | 8
9 | Resource Name 09 | Sr Design Engineer | 8
10 | Resource Name 10 | Sr Design Engineer | 8